## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 01. Account Management | 1.03 | Modify Account Information | Search for proper validation methods for account fields | 2024-10-25 | 2024-10-30 | 100% | Sunil Chinthaparthi
2 | 01. Account Management | 1.03 | Modify Account Information | Set up backend logic for account updates | 2024-10-30 | 2024-11-06 | 100% | Rohit Bhogaraju
3 | 01. Account Management | 1.03 | Modify Account Information | Develop and integrate account modification | 2024-10-28 | 2024-11-06 | 100% | Rohit Bhogaraju
4 | 01. Account Management | 1.03 | Modify Account Information | Implement user interface for modifying account information | 2024-10-28 | 2024-11-05 | 100% | Singh Sakshi
5 | 01. Account Management | 1.03 | Modify Account Information | Implement field validation for account fields | 2024-11-05 | 2024-11-10 | 100% | Mahankali Nehal
6 | 01. Account Management | 1.03 | Modify Account Information | Develop test cases for account modification validation | 2024-11-05 | 2024-11-10 | 100% | Mahankali Nehal
7 | 01. Account Management | 1.03 | Modify Account Information | Test account modification functionality for accuracy | 2024-11-05 | 2024-11-10 | 100% | Zaheer Abbas
8 | 02. Job Seach and Application | 2.02 | Apply For Jobs | Search for job applications in the data base | 2024-10-25 | 2024-10-30 | 100% | Rohit Bhogaraju
9 | 02. Job Seach and Application | 2.02 | Apply For Jobs | Implement job application submission Functionality | 2024-10-28 | 2024-11-05 | 100% | Rohit Bhogaraju
10 | 02. Job Seach and Application | 2.02 | Apply For Jobs | Design user interface for job application submission | 2024-10-28 | 2024-10-05 | 100% | Sunil Chinthaparthi
11 | 02. Job Seach and Application | 2.02 | Apply For Jobs | Develop functionality to validate job application fields | 2024-10-25 | 2024-10-30 | 100% | Sunil Chinthaparthi
12 | 02. Job Seach and Application | 2.02 | Apply For Jobs | Test job application submission functionality | 2024-11-08 | 2024-11-10 | 100% | Zaheer Abbas
13 | 02. Job Seach and Application | 2.03 | Track Application Status | Set up database schema to store application status | 2024-10-25 | 2024-10-30 | 100% | Rohit Bhogaraju
14 | 02. Job Seach and Application | 2.03 | Track Application Status | Develop front-end interface for viewing application status | 2024-10-28 | 2024-11-08 | 100% | Sunil Chinthaparthi
15 | 02. Job Seach and Application | 2.03 | Track Application Status | Implement functionality for updating application status | 2024-11-05 | 11/10/24 | 100% | Venkat Sanjay
16 | 02. Job Seach and Application | 2.03 | Track Application Status | Test application status functionality | 2024-11-06 | 2024-11-13 | 100% | Kalavakuri Manasa Sai
17 | 02. Job Seach and Application | 2.04 | Save Job Searches | Add functionality to view saved jobs | 2024-10-25 | 2024-10-30 | 100% | Singh Sakshi
18 | 02. Job Seach and Application | 2.04 | Save Job Searches | Test saved search functionality | 2024-11-08 | 2024-11-13 | 100% | Syed Vaseem
19 | 02. Job Seach and Application | 2.04 | Save Job Searches | Implement a check to prevent users from saving job listings that have expired | 2024-11-08 | 2024-11-13 | 100% | Rohit Bhogaraju
20 | 02. Job Seach and Application | 2.04 | Save Job Searches | Verify saving and retrieving searches efficiently | 2024-11-08 | 2024-11-13 | 100% | Mahankali Nehal
21 | 02. Job Seach and Application | 2.06 | Receive Email Notifications | Develop email notification system and configure triggers | 2024-11-08 | 2024-11-13 | 100% | Rohit Bhogaraju
22 | 02. Job Seach and Application | 2.06 | Receive Email Notifications | Set up and standard templates test email for different notification types | 2024-10-25 | 2024-10-30 | 100% | Rohit Bhogaraju
23 | 02. Job Seach and Application | 2.06 | Receive Email Notifications | Verify notification triggers | 2024-11-08 | 2024-11-13 | 100% | Syed Vaseem

## S3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 03.Job Posting and Management | 3.02 | Create Job Listings | Research optimal search algorithms and filtering methods. | 2024-11-14 | 2024-11-20 | 100% | Sunil Chinthaparthi
2 | 03.Job Posting and Management | 3.02 | Create Job Listings | Set up back-end functionality for searching candidates. | 2024-11-14 | 2024-11-20 | 100% | Rohit Bhogaraju
3 | 03.Job Posting and Management | 3.02 | Create Job Listings | Develop and integrate front-end search filters and interface. | 2024-11-21 | 2024-11-28 | 100% | Rohit Bhogaraju
4 | 03.Job Posting and Management | 3.02 | Create Job Listings | Implement field validation for search input fields. | 2024-11-14 | 2024-11-20 | 100% | Singh Sakshi
5 | 03.Job Posting and Management | 3.02 | Create Job Listings | Produce test specifications for search functionality. | 2024-11-21 | 2024-11-28 | 100% | Mahankali Nehal
6 | 03.Job Posting and Management | 3.02 | Create Job Listings | Test search functionality for accuracy and performance. | 2024-11-21 | 2024-11-28 | 100% | Syed Vaseem
7 | 03.Job Posting and Management | 3.03 | Update Job Listings | Research validation techniques for job listing fields. | 2024-11-14 | 2024-11-20 | 100% | Sunil Chinthaparthi
8 | 03.Job Posting and Management | 3.03 | Update Job Listings | Set up back-end logic for updating job listings. | 2024-11-21 | 2024-11-28 | 100% | Rohit Bhogaraju
9 | 03.Job Posting and Management | 3.03 | Update Job Listings | Implement a user-friendly interface for updating job listings. | 2024-11-21 | 2024-11-28 | 100% | Zaheer Abbas
10 | 03.Job Posting and Management | 3.03 | Update Job Listings | Validate all fields for job updates, including title, salary, and description. | 2024-11-21 | 2024-11-28 | 100% | Singh Sakshi
11 | 03.Job Posting and Management | 3.03 | Update Job Listings | Produce test specifications for job update functionality. | 2024-11-21 | 2024-11-28 | 100% | Mahankali Nehal
12 | 03.Job Posting and Management | 3.03 | Update Job Listings | Test job update functionality for both success and edge cases. | 2024-11-21 | 2024-11-28 | 100% | Syed Vaseem
13 | 03.Job Posting and Management | 3.04 | Delete Job Listings | Research confirmation modal designs and best practices. | 2024-11-14 | 2024-11-20 | 100% | Sunil Chinthaparthi
14 | 03.Job Posting and Management | 3.04 | Delete Job Listings | Set up back-end functionality to remove job listings. | 2024-11-21 | 2024-11-28 | 100% | Rohit Bhogaraju
15 | 03.Job Posting and Management | 3.04 | Delete Job Listings | Develop a front-end interface for listing deletion | 2024-11-21 | 2024-11-28 | 100% | Zaheer Abbas
16 | 03.Job Posting and Management | 3.04 | Delete Job Listings | Produce test specifications for listing deletion functionality. | 2024-11-28 | 2024-12-05 | 100% | Kalavakuri Manasa Sai
17 | 03.Job Posting and Management | 3.04 | Delete Job Listings | Test deletion functionality to ensure job listings are removed correctly. | 2024-11-28 | 2024-12-05 | 100% | Venkat Sanjay
18 | 04. Subscription and Payments | 4.01 | Manage Subscription Plans | Research subscription plan validation techniques | 2024-11-14 | 2024-11-20 | 100% | Sunil Chinthaparthi
19 | 04. Subscription and Payments | 4.01 | Manage Subscription Plans | Set up back-end logic for managing subscription plans | 2024-11-21 | 2024-11-28 | 100% | Rohit Bhogaraju
20 | 04. Subscription and Payments | 4.01 | Manage Subscription Plans | Implement a user-friendly interface for subscription plan management. | 2024-11-28 | 2024-12-05 | 100% | Zaheer Abbas
21 | 04. Subscription and Payments | 4.01 | Manage Subscription Plans | Produce test specifications for subscription plan management. | 2024-11-28 | 2024-12-05 | 100% | Kalavakuri Manasa Sai
22 | 04. Subscription and Payments | 4.01 | Manage Subscription Plans | Test subscription plan creation, updates, and deletions. | 2024-11-28 | 2024-12-05 | 100% | Venkat Sanjay
23 | 04. Subscription and Payments | 4.02 | Process the Payments | Research payment gateway APIs, choose an integration method. | 2024-11-14 | 2024-11-20 | 100% | Sunil Chinthaparthi
24 | 04. Subscription and Payments | 4.02 | Process the Payments | Set up API integration with selected payment gateways | 2024-11-21 | 2024-11-28 | 100% | Rohit Bhogaraju
25 | 04. Subscription and Payments | 4.02 | Process the Payments | Implement field validation for payment details | 2024-11-28 | 2024-12-05 | 100% | Rohit Bhogaraju
26 | 04. Subscription and Payments | 4.02 | Process the Payments | Produce test specifications for payment processing functionality. | 2024-11-28 | 2024-12-05 | 100% | Kalavakuri Manasa Sai
27 | 04. Subscription and Payments | 4.02 | Process the Payments | Test various payment scenarios | 2024-11-28 | 2024-12-05 | 100% | Sunil Chinthaparthi