## Sheet1
HIREHUB
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/24/2023 | SPRINT2 - 11/14/2023 | SPRINT3 - 12/12/2023
01. Account Management | 01.01 Sign Up for an Account | 4 | x
| 01.02 Login to an Account | 4 | x
| 01.03 Modify Account Information | 3 |  | x
| 01.04 Reset Passwords | 4 | x
| 01.05 Delete Accounts | 2
02. Job Search and Application | 02.01 Search Jobs with Filters | 4 | x
| 02.02 Apply for Jobs | 4 |  | x
| 02.03 Track Applicaion Status | 4 |  | x | x
| 02.04 Save Job Searches | 4 |  | x
| 02.05 Access Career Resources | 2
| 02.06 Receive Email Notifications | 4 |  | x
03. Job Posting and Management | 03.01 Create Job Listings | 4 | x
| 03.02 Search for Candidates | 4 |  |  | x
| 03.03 Update Job Listings | 4 |  |  | x
| 03.04 Delete Job Listings | 4 |  |  | x
04. Subscription and Payments | 04.01 Manage Subscription Plans | 4 |  | x
| 04.02 Process the Payments | 4 |  |  | x
| 04.03 Track Active Subscriptions | 2
05. Reporting & Analytics | 05.01 Track Job Posting Performance | 3
| 5.02 Generate Financial Reports | 4
06. Customer Support | 06.01 Manage Support Tickets | 4
| 06.02 Assist with Profile Updates | 3
| 06.03 Track and Resolve Issues | 4
07. Sales Support | 07.01 Onboard New Employers | 4
| 07.02 SManage Employer Subscriptions | 4
| 07.03 Provide Performance Insights | 2
08. Advertising Management | 08.01 Choose Ad Campaign Packages (Basic, Regular and Premium) | 4
| 08.02 Set Ad Budget and Metrics | 3
|  | VELOCITY: | 20 | 23 | 20